## Sheet1
Level | 0 | 1 | 2 | 3 | Remarks
AIM workshop (Teams) | No Team(s) trained | Some of the Team(s) are trained |  | All of the Team(s) are trained | Yes/No/Partial No Scoring
AIM workshop (PLTs) | No PLT(s) trained | Some of the PLT(s) are trained |  | All PLT(s) are trained | Yes/No/Partial No Scoring
Certification – PO | No PO certified | Some POs certified |  | All POs certified | Yes/No/Partial No Scoring
Certification – SM | No SM certified | Some SMs certified |  | All SMs certified | Yes/No/Partial No Scoring
Multi component team | Component teams w/o SLT | Component teams w/ SLT (or Uber-PLT) | Solution level feature teams per release | Permanent solution feature teams | Feature means end-to-end customer value. Feature teams might require teams re-structuring. No Scoring.
Product Owner | No product owner | Just introduced (<6M) | Independent but not empowered | Empowered to work independently | Independent: can take the right AIM decisions. (Not working in a SILO, working together as a Solution.) Empowered: allowed to take the right AM decisions
Scrum Master | No scrum master | Just introduced (<6M) | Independent but not empowered | Empowered to work independently | Independent: can take the right AIM decisions. (Not working in a SILO, working together as a Solution.) Empowered: allowed to take the right AM decisions
Multi Functional Team | Separate dev & QA teams | Dev + QA teams | Dev + QA + DevOps teams | Dev + QA + DevOps + Doc teams | Doc: documentation person is part of the sprint working with the Scrum Team (+ DoD includes documentation)
DoD | No DoD | Defined DoD (or part of DoD followed always) | DoD followed sometimes | DoD followed always | Defined = agreement by all the relevant stakeholders, based on the AIM baseline
DoR | No DoR | Defined DoR (or part of DoR followed always) | DoR followed sometimes | DoR followed always | Defined = agreement by all the relevant stakeholders, based on the AIM baseline
Scrum ceremonies | Not Defined | Calendar published | Calendar followed sometimes OR calendar followed always, but some events are not conducted properly | Calendar followed always and events are being done properly using the AIM guidelines | Daily, Planning, Refinement, Retro, Review
Scrum area | Not set-up | Scrum area created | Scrum area used sometimes | Scrum area used extensively | Physical/Virtual Scrum Area is being used on daily basis. The following is being visible and managed: impediments, sprint goal, sprint backlog workflow
Story Points | Not used / Hours converted to points | Started using complexity-based story points | Able to demonstrate predictable velocity sometimes | Demonstrates predictable velocity consistently | Looking for predictability, not consistency, review the expected vs. actual in velocity chart, not story pointing defects and spikes
Tasking | No detailed tasking | Started doing low level tasks | Sometimes all tasks are defined on first day of sprint | All tasks are defined on first day consistently | Tasking is a high-level breakdown of a story into testable pieces (<2d). This encourages WIP-limit and daily collaboration. In case tasking is hard, consider a spike.
Backlog grooming (sprint) | No continuous story grooming | Always grooming one sprint ahead | Always grooming 2 sprints ahead | Always grooming 3 sprints ahead | Match DoR and sized
Backlog grooming (release) | No continuous release planning | Always grooming one release ahead at 50% confidence | Always planning one release at 50% + 1 releases at 20% | Always planning one release at 50% + 2 releases at 20% | The PLT/SLT Kanban board can provide a good view. Shorter releases are easier to predict.
Demo | Never / rarely | Done once in a while. | Done usually OR done only for part of the stories | Done every sprint for each completed story! PO accepts/rejects | Demonstrate all the completed stories. Accept/reject all stories (user value, tech, spike).
Retro | Never / rarely | Done every sprint, but the forum is inadequate | Done every sprint, but not always at least one improvement is implemented | Done every sprint & at least one improvement is implemented each time | ‘Inadequate’ means that the forum is different from the Scrum team – e.g. PO is not invited, non-Scrum-team people like managers are participating. Yellow and Green categories assume the forum is correct.
Unified backlog | Multiple backlogs | Created unified backlog | Demonstrated consistent single backlog maintained over 6 sprints | Demonstrated consistent single backlog maintained over 12 sprints | Regardless of user-value
Personas | No personas | Built personas for a release | Demonstrated personas usage over 2 releases | Demonstrated persona driven release planning consistently! (>3 releases) | Backlog according to user value
Story mapping | No story mapping | Story mapping done for one release | Demonstrated consistent story mapping over 2 releases | Demonstrated consistent story mapping over 3 releases | Map of stories and sprints aligned by PLM-PO-Team. We are looking for user-value stories that are prioritized (as opposed to Feature prioritization). Our observation is that story mapping is the main technique achieving that.
Work-Item templates | AIM backlog work-item template not adopted | Started using AIM backlog work-item templates OR templates being used sometimes | Demonstrated backlog work-item writing consistently over 6 sprints | Demonstrated backlog work-item writing consistently over 12 sprints | Each scoring level refers to all 3 types of work-item (user story, technical story, spike).
Tech debt strategy | No strategy | Good strategy defined | Good strategy implemented consistently over 6 sprints | Good strategy implemented consistently over 12 sprints | Identify the tech debt, capture that in JIRA, story point it, and define a threshold
Defect management strategy | No strategy | Good strategy defined | Good strategy implemented consistently over 6 sprints | Good strategy implemented consistently over 12 sprints | Procedure for handling defects. Defining defect % reduction target for a sprint/release. Team targets red/yellow zone new content defects within the sprint.
AIM JIRA structure | Not adopted AIM JIRA scheme |  |  | Adopted AIM JIRA scheme | There are only 2 JIRA schemes at Avaya: AGSP and AIM.
Release tracker | No release tracking dashboard | Have product specific release tracker |  | Adopted AIM recommended release tracker | Gathering AIM JIRA metrics as defined here
Sprint burndown | No burndown or hours-based sprint burndown | Started tracking story point-based burndown | Few stories getting done & accepted earlier within a sprint | Stories always getting ‘done’ one after another throughout the sprint!
BDD | Not practiced | Practiced sometimes | Demonstrated incremental development using BDD consistently over 6 sprints! | Demonstrated incremental development using BDD consistently over 12 sprints! | Delivering a story behavior (use case slice) one after the other, according to the acceptance criteria. This category doesn’t refer to automation or Cucumber.
TDD | Not practiced | Practiced sometimes | Demonstrated TDD consistently over 6 sprints! | Demonstrated TDD consistently over 12 sprints!
Test automation | Test automation not mandatory for doneness | All new code is automated for doneness | Legacy code automation strategy implemented – 50% tests automated | No manual tests required!
CI/CD | No CI/CD pipeline | Basic pipeline – build, test & deploy on every check-in (or at least every night) | Enhanced pipeline – feature branches, pull requests covered. One-click promotion to higher environments | Advanced pipeline – check-in to prod, blue-green deployments | O->Y: CI/CD not only on master branch, but also on feature branch. Higher-environment is used by real users.
Shift-left adoption | Aligned with concept but not practiced | Demonstrates bug count found in solution testing going down | Demonstrates customer found bug count in going down | Customer found bugs close to zero!
Single branch strategy | Multiple code branch strategy (per-person branch) | Uses branch per story, merge-able to master (or dev branch) | Uses branch per story, merge-able to master (no dev branch) | Uses branch per sub-task, merge-able to master (without breaking anything else) | Single master branch strategy (always potentially releasable).
Reducing WIP | Most stories are in progress on any given day of sprint | No more than 75% stories are in progress on any given day of sprint | No more than 50% stories are in progress on any given day of sprint | No more than 25% stories are in progress on any given day of sprint! | Encouraging breaking stories into small ones. Teams that are not completing at least 80% of their story-points, are not eligible for this scoring and should be marked red.
Engineering 360 | No engineering 360 done |  | Adopted AIM engineering 360 template and did first 360 | Demonstrated engineering 360 consistently over 12 sprints | Using a variation of AIM engineering 360 template for review in a PLT+ forum.
Customer engagement | No customer engagement strategy | Customer engagement strategy defined! | Engaged customer consistently over 6 sprints | Engaged customer consistently over 12 sprints | Alpha/Beta fixed date milestones are not enough. Continuously show progress and get feedback from the customer. Negotiate adaptions in the plan.
Time to Value Delivery | Customer value items are usually not delivered within single sprint | Customer value items are delivered by the end of each sprint | A few customer value items are delivered earlier within a sprint | Customer value items are always delivered one after another throughout the sprint | For component teams, collaboration is required cross-teams in order to deliver value within a sprint